## KEY
| VERY LOW (1) | LOW (2) | MEDIUM (3) | HIGH (4) | VERY HIGH (5)
VERY LOW (1) | 1 | 2 | 3 | 4 | 5 | < 3 | Negligable Risk
LOW (2) | 2 | 4 | 6 | 8 | 10 | 3 TO 5 | Consideration
MEDIUM (3) | 3 | 6 | 9 | 12 | 15 | 6 TO 10 | Concern/Warning
HIGH (4) | 4 | 8 | 12 | 16 | 20 | 11 TO 16 | Significant Issue
VERY HIGH (5) | 5 | 10 | 15 | 20 | 25 | > 16 | Catestrophic

## Risk Assessment
DESCRIPTION | EVALUATION | LIKELIHOOD | IMPACT | SCORE | RESPONSE | CONTROL | NEW LIKELIHOOD | NEW IMPACT | NEW SCORE
Failure to meet schedule | Unable to deliver | 2 | 5 | 10 | Communicate with stakeholder | Monitor & plan progress | 1 | 4 | 4
Update breaks product | Software no long meets MVP | 3 | 4 | 12 | Restore from Git | Test all code before deployment | 2 | 2 | 4
Laptop breaks | Unable to do anything | 4 | 5 | 20 | Contact stakeholder, try to aquire substitute | Reduce strain put on laptop | 3 | 4 | 12
SQL password is shared | GDPR; leaked data | 5 | 2 | 10 | Change passwords, add security measures | Review all shared data prior to sharing | 4 | 1 | 4